## Saragadam Vara Sai Ram
Sprint Planning Sheet
Online Salon Service
Task | Priority | Status | Start date | End date | Notes
Eureka-Service | P1 | Completed | 2024-08-24 | 2024-08-24 | Create Eureka Server
Booking-Microservice | P1 | Completed | 2024-08-24 | 2024-08-25 | Create Booking-Microservice and connect to DataBase and test it working or not
Customer-MicroService | P1 | Completed | 2024-08-25 | 2024-08-25 | Create Customer-Microservice and connect to DataBase and test it working or not
Service-Microservice | P2 | Completed | 2024-08-26 | 2024-08-26 | Create a Service-Microservice and connect to DataBase and test it
Staff-Microservice | P2 | Completed | 2024-08-26 | 2024-08-26 | Create a Staff-Microservice and connect to DataBase and test it
Authentication-Service | P1 | Completed | 2024-08-27 | 2024-08-28 | test the Authentication-Service is working with register,Token genration and token validation
API-Gateway | P3 | Completed | 2024-08-29 | 2024-08-29 | Connect all the Microservice and Authentication-Service to Gateway and test it
Junit | P3 | Completed | 2024-08-30 | 2024-08-31 | Test the Junit for all the services
PPT | P2 | Completed | 2024-08-31 | 2024-09-01 | create ppt for presentation of project
Documentation | P2 | Completed | 2024-09-01 | 2024-09-01 | source code, flow diagrams and pdfs of output to subit on platform in zip
GIT Implementation | P3 | Completed | 2024-09-02 | 2024-09-02 | Submit Source code on Github after completion of project

## User
Task | Priority | Status | Start date | End date | Notes
Eureka-Service | P0 | Completed | 2024-08-21 | 2024-08-21 | Create Eureka Server
Employee-Service | P0 | Completed | 2024-08-21 | 2024-08-22 | Create Employee-service and connect to a DB
Department-Service | P1 | Completed | 2024-08-21 | 2024-08-22 | Create Department table in DB, create a microservice 'Department-Service' and connect to Department table.
Performance-Service | P2 | Completed | 2024-08-22 | 2024-08-22 | Create Performance-Service microservice
Task-Service | P2 | Completed | 2024-08-23 | 2024-08-23
API-Gateway-Service | P2 | Completed | 2024-08-24 | 2024-08-25
Authentication-Service | P1 | Completed | 2024-08-24
Junit | P3 | Completed | 2024-08-30 | 2024-08-31
GIT Implementation
PPT